## Issues Report
Title | Description | Issue ID | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Login Screen | This is a screen which allows the user to enter email & password to login to manage user in the system. | 1 | Open | Manhnv | 2023-02-04 | 2023-02-06 | iter1 | Done | Login Screen
Write SRS for Login screen |  | 2 | Open | Manhnv | 2023-02-04 | 2023-02-06 | iter1 | Done | Login Screen
Write SDS for Login screen |  | 3 | Open | Manhnv | 2023-02-04 | 2023-02-06 | iter1 | Done | Login Screen
Write Code for Login screen |  | 4 | Open | Manhnv | 2023-02-04 | 2023-02-06 | iter1 | Done | Login Screen
Integrate Login screen with others |  | 5 | Open | Manhnv | 2023-02-04 | 2023-02-10 | iter1 | Done | Login Screen
Admin Manage User Page | This is a screen which allows the admin to view and manage users in the system. | 6 | Open | Namvt | 2023-02-04 | 2023-02-08 | iter1 | Deleted | Admin Manage User Page
Write SRS for Admin Manage User Page |  | 7 | Open | Namvt | 2023-02-04 | 2023-02-07 | iter1 | Deleted | Admin Manage User Page
Write SDS for Admin Manage User Page |  | 8 | Open | Namvt | 2023-02-04 | 2023-02-07 | iter1 | Deleted | Admin Manage User Page
Write Code for Admin Manage User Page |  | 9 | Open | Namvt | 2023-02-04 | 2023-02-08 | iter1 | Deleted | Admin Manage User Page
Integrate Admin Manage User Page with Others |  | 10 | Open | Namvt | 2023-02-04 | 2023-02-10 | iter1 | Deleted | Admin Manage User Page
Admin Change Activate User | This is a function which allows the admin to change activate user to make user can login to the system or not. | 11 | Open | Datna | 2023-02-04 | 2023-02-11 | iter2 | Deleted | Admin Change Activate User
Write SRS for Admin Change Activate User |  | 12 | Open | Datna | 2023-02-04 | 2023-02-11 | iter2 | Deleted | Admin Change Activate User
Write SDS for Admin Change Activate User |  | 13 | Open | Datna | 2023-02-04 | 2023-02-11 | iter2 | Deleted | Admin Change Activate User
Write Code for Admin Change Activate User |  | 14 | Open | Datna | 2023-02-04 | 2023-02-11 | iter2 | Deleted | Admin Change Activate User
Integrate Admin Change Activate User with Others |  | 15 | Open | Datna | 2023-02-04 | 2023-02-11 | iter2 | Deleted | Admin Change Activate User
User Register | This is a function which allows the user to register a new account include: new information, email and password. | 16 | Open | Hunghm | 2023-02-04 | 2023-02-10 | iter1 | Done | User Register
Write SRS for User Register |  | 17 | Open | Hunghm | 2023-02-04 | 2023-02-10 | iter1 | Done | User Register
Write SDS for User Register |  | 18 | Open | Hunghm | 2023-02-04 | 2023-02-10 | iter1 | Done | User Register
Write Code for User Register |  | 19 | Open | Hunghm | 2023-02-04 | 2023-02-10 | iter1 | Done | User Register
Integrate User Register with Others |  | 20 | Open | Hunghm | 2023-02-04 | 2023-02-10 | iter1 | Done | User Register
User Home Page | The screen displays a list of debtors (name, phone number,...), users can add debtors, add debt slip details,… | 21 | Open | Hungnb | 2023-02-04 | 2023-02-08 | iter1 | Doing | User Home Page
Write SRS for User Home Page |  | 22 | Open | Hungnb | 2023-02-04 | 2023-02-07 | iter1 | Doing | User Home Page
Write SDS for User Home Page |  | 23 | Open | Hungnb | 2023-02-04 | 2023-02-07 | iter1 | Doing | User Home Page
Write Code for User Home Page |  | 24 | Open | Hungnb | 2023-02-04 | 2023-02-08 | iter1 | Doing | User Home Page
Integrate User Home Page with Others |  | 25 | Open | Hungnb | 2023-02-04 | 2023-02-10 | iter1 | Doing | User Home Page
User Change Password | The screen that allows the user to change the account's password | 31 | Open | Manhnv | 2023-02-04 | 2023-02-14 | iter2 | Doing | User Change Password
Write SRS for User Change Password |  | 32 | Open | Manhnv | 2023-02-04 | 2023-02-14 | iter2 | Doing | User Change Password
Write SDS for User Change Password |  | 33 | Open | Manhnv | 2023-02-04 | 2023-02-14 | iter2 | Doing | User Change Password
Write Code for User Change Password |  | 34 | Open | Manhnv | 2023-02-04 | 2023-02-14 | iter2 | Doing | User Change Password
Integrate User Change Password with Others |  | 35 | Open | Manhnv | 2023-02-04 | 2023-02-14 | iter2 | Doing | User Change Password
User Create Car | This is a function which allow user create a new Car for manage | 36 | Open | Hunghm | 2023-02-04 | 2023-02-16 | iter2 | Doing | User Create Car
Write SRS for User Create car |  | 37 | Open | Hunghm | 2023-02-04 | 2023-02-16 | iter2 | Doing | User Create Car
Write SDS for User Create car |  | 38 | Open | Hunghm | 2023-02-04 | 2023-02-16 | iter2 | Doing | User Create Car
Write Code for User Create car |  | 39 | Open | Hunghm | 2023-02-04 | 2023-02-16 | iter2 | Doing | User Create Car
Integrate User Create car with Others |  | 40 | Open | Hunghm | 2023-02-04 | 2023-02-16 | iter2 | Doing | User Create Car
User View List Car | This is a function which allow user view all car that user created. | 41 | Open | Hungnb | 2023-02-04 | 2023-02-11 | iter1 | Doing | User View List Car
Write SRS for User View List car |  | 42 | Open | Hungnb | 2023-02-04 | 2023-02-11 | iter1 | Doing | User View List Car
Write SDS for User View List car |  | 43 | Open | Hungnb | 2023-02-04 | 2023-02-11 | iter1 | Doing | User View List Car
Write Code for User View List car |  | 44 | Open | Hungnb | 2023-02-04 | 2023-02-11 | iter1 | Doing | User View List Car
Integrate User View Listcar with Others |  | 45 | Open | Hungnb | 2023-02-04 | 2023-02-11 | iter1 | Doing | User View List Car
User Search Car | This is a function which help user find car by name, money, date, description,... in their car list. | 46 | Open | Datna | 2023-02-04 | 2023-02-17 | iter3 | Done | User Search Car
Write SRS for User Search Car |  | 47 | Open | Datna | 2023-02-04 | 2023-02-17 | iter3 | Done | User Search Car
Write SDS for User Search Car |  | 48 | Open | Datna | 2023-02-04 | 2023-02-17 | iter3 | Done | User Search Car
Write Code for User Search Car |  | 49 | Open | Datna | 2023-02-04 | 2023-02-17 | iter3 | Doing | User Search Car
Integrate User Search Car with Others |  | 50 | Open | Datna | 2023-02-04 | 2023-02-17 | iter3 | Doing | User Search Car
User View Detail Car | This is a function which allow user see details about car. | 51 | Open | Namvt | 2023-02-04 | 2023-02-20 | iter3 | Doing | User View Detail Car
Write SRS for User View Detail Car |  | 52 | Open | Namvt | 2023-02-04 | 2023-02-20 | iter3 | Doing | User View Detail Car
Write SDS for User View Detail Car |  | 53 | Open | Namvt | 2023-02-04 | 2023-02-20 | iter3 | Doing | User View Detail Car
Write Code for User View Detail Car |  | 54 | Open | Namvt | 2023-02-04 | 2023-02-20 | iter3 | Doing | User View Detail Car
Integrate User View Detail Car with Others |  | 55 | Open | Namvt | 2023-02-04 | 2023-02-20 | iter3 | Doing | User View Detail Car
User Update Car | This is a function which allow users update information about Car. | 56 | Open | Manhnv | 2023-02-04 | 2023-02-21 | iter2 | Doing | User Update Car
Write SRS for User Update Car |  | 57 | Open | Manhnv | 2023-02-04 | 2023-02-21 | iter2 | Doing | User Update Car
Write SDS for User Update Car |  | 58 | Open | Manhnv | 2023-02-04 | 2023-02-21 | iter2 | Doing | User Update Car
Write Code for User Update Car |  | 59 | Open | Manhnv | 2023-02-04 | 2023-02-21 | iter2 | Doing | User Update Car
Integrate User Update Car with Others |  | 60 | Open | Manhnv | 2023-02-04 | 2023-02-21 | iter2 | Doing | User Update Car
User Create Car | This is a function which allows the user to create the Car. | 61 | Open | Hungnb | 2023-02-04 | 2023-02-22 | iter3 | Done | User Create Car
Write SRS for User Create Car |  | 62 | Open | Hungnb | 2023-02-04 | 2023-02-22 | iter3 | Done | User Create Car
Write SDS for User Create Car |  | 63 | Open | Hungn | 2023-02-04 | 2023-02-22 | iter3 | Done | User Create Car
Write Code for User Create Car |  | 64 | Open | Hungnb | 2023-02-04 | 2023-02-22 | iter3 | Done | User Create Car
Integrate User Create Car with Others |  | 65 | Open | Hungnb | 2023-02-04 | 2023-02-22 | iter3 | Done | User Create Car
User Delete Car | This is a function which allows user delete the Car from detail Car | 76 | Open | Hunghm | 2023-02-04 | 2023-02-25 | iter3 | Doing | User Delete Car
Write SRS for User Delete Car |  | 77 | Open | Hunghm | 2023-02-04 | 2023-02-25 | iter3 | Doing | User Delete Car
Write SDS for User Delete Car |  | 78 | Open | Hunghm | 2023-02-04 | 2023-02-25 | iter3 | Doing | User Delete Car
Write Code for User Delete Car |  | 79 | Open | Hunghm | 2023-02-04 | 2023-02-25 | iter3 | Doing | User Delete Car
Integrate User Delete Car with Others |  | 80 | Open | Hunghm | 2023-02-04 | 2023-02-25 | iter3 | Doing | User Delete Car